## Readiness
Manufacturing Readiness Review — LC-1000
Readiness checklist across engineering, supply chain, manufacturing, quality, test and documentation, with open actions.
DOCUMENT ID | MQA-MRR-001
REVISION | A
DATE | September 2026
PREPARED BY | Mohammad Al-Araidah
STATUS | Issued for independent engineering study
CLASSIFICATION | Synthetic data — not for production use
INDEPENDENT ENGINEERING STUDY — the supplier, equipment, specifications and all results in this workbook are synthetic. Not design guidance, not a compliance assessment against any standard, and not for use on a production programme.
Overall: READY WITH ACTIONS
SECTION | READINESS ITEM | STATUS | BASIS
Engineering release | Drawings approved and released at a controlled revision | Ready | Full drawing set released; revision list issued to manufacturing.
Engineering release | Bill of material released and matched to the drawing set | Ready | BOM reconciled against the released drawings line by line.
Engineering release | Specifications and referenced standards controlled | Ready | Specification register issued with the revision of each referenced document.
Engineering release | Software / firmware revision defined for PLC and instruments | Action | PLC application revision is defined; instrument firmware revisions are not yet recorded in the configuration list.
Supply chain | Critical components sourced from approved sub-tier suppliers | Ready | Pumps, heat exchanger, instrumentation and valves sourced from the approved list.
Supply chain | Long-lead material on site or confirmed to the build schedule | Ready | Heat exchanger and pump deliveries confirmed ahead of the fabrication start.
Supply chain | Sub-tier quality requirements flowed down | Action | Certificate requirements are flowed down; the weld traceability requirement from the qualification conditions is not yet in the sub-tier fabrication purchase order.
Manufacturing | Work instructions released for every operation in the routing | Ready | Instructions released; the two operations flagged during qualification now include a component verification step.
Manufacturing | Tooling and fixtures available and verified | Ready | Fit-up fixtures and test connections available and checked against the drawings.
Manufacturing | Operators qualified for their assigned operations | Ready | Qualification records current for assembly, brazing and electrical operations.
Manufacturing | Welding procedures approved and welders currently qualified | Ready | WPS and supporting PQR in place for the production joints; welder qualifications current.
Quality | Inspection and test plan released and accepted by the supplier | Ready | ITP MQA-ITP-001 Rev A issued and accepted, including the owner hold points.
Quality | Inspection and test equipment calibrated | Action | Test-area instruments returned to current calibration per the qualification conditions; the escalating recall system is implemented but has not yet completed one full recall cycle.
Quality | Nonconformance process defined including notification to the owner | Ready | Revised NCR procedure includes effectiveness verification and owner notification for hold-point nonconformances.
Quality | Traceability method validated to skid serial number | Ready | Weld records now keyed to joint identifier, welder and WPS; validated on the first article.
Test | FAT equipment and test loop available | Ready | Test loop capable of design flow with adjustable resistance to set the operating point.
Test | Test instrumentation calibrated and of adequate range and resolution | Ready | Flow, pressure, differential pressure and temperature instruments calibrated, with ranges appropriate to the acceptance values.
Test | FAT protocol approved by both parties | Ready | MQA-FAT-001 Rev A approved, including pass / pass-with-deviation / fail definitions.
Documentation | Turnover documentation index defined and agreed | Ready | Index issued listing every document required for release, with the responsible party for each.
Documentation | Certificates identified for material, pressure test and calibration | Ready | Certificate list agreed and mapped to ITP record requirements.
Documentation | Test record templates approved before test execution | Ready | Templates approved so results are recorded against acceptance criteria rather than transcribed afterwards.

## Open actions
Manufacturing Readiness Review — LC-1000
Readiness checklist across engineering, supply chain, manufacturing, quality, test and documentation, with open actions.
DOCUMENT ID | MQA-MRR-001
REVISION | A
DATE | September 2026
PREPARED BY | Mohammad Al-Araidah
STATUS | Issued for independent engineering study
CLASSIFICATION | Synthetic data — not for production use
INDEPENDENT ENGINEERING STUDY — the supplier, equipment, specifications and all results in this workbook are synthetic. Not design guidance, not a compliance assessment against any standard, and not for use on a production programme.
REF | ACTION | OWNER | DUE | GATE IT BLOCKS | CLOSURE EVIDENCE
MRR-01 | Record instrument firmware revisions in the configuration list and freeze the as-built configuration. | Supplier controls engineering | Before controls testing | Controls section of FAT
MRR-02 | Add the weld traceability requirement to the sub-tier fabrication purchase order and confirm acceptance. | Supplier procurement | Before fabrication release | Fabrication start
MRR-03 | Complete one full recall cycle on the calibration system and provide the resulting status report. | Supplier quality | Before FAT | FAT hold points